TECHNICAL PROPOSAL

Innovic ERP

Migration to Web-Scale Architecture

From single-file HTML to production SaaS-grade platform

| Project | Innovic ERP — Architecture Migration |
| --- | --- |
| Current State | 29,000-line HTML file backed by Firebase Firestore (single-document-per-collection) |
| Target State | React SPA + Fastify API + Supabase Postgres (Mumbai region) |
| User Scale | 15–20 concurrent users today, scales to 100 without rearchitecting |
| Data Volume | ~50 GB ultimate (5–15 GB Postgres, 35–45 GB file storage) |
| Timeline | 12 weeks, parallel-run migration (zero downtime) |
| Monthly Cost | ~₹2,800 / month (~$33 USD) at full scale |
| Document Date | 29 April 2026 |

# Table of Contents

| 1. | Executive Summary | 3 |
| --- | --- | --- |

| 2. | Current System Diagnosis | 4 |
| --- | --- | --- |

| 3. | Target Architecture | 5 |
| --- | --- | --- |

| 4. | Why Supabase (Decision Rationale) | 7 |
| --- | --- | --- |

| 5. | Database Schema Design | 8 |
| --- | --- | --- |

| 6. | Migration Plan — 12 Week Roadmap | 10 |
| --- | --- | --- |

| 7. | Cost Breakdown | 13 |
| --- | --- | --- |

| 8. | Operating Rules (Non-Negotiable) | 14 |
| --- | --- | --- |

| 9. | Risks & Mitigation | 15 |
| --- | --- | --- |

| 10. | Deliverables & Acceptance Criteria | 16 |
| --- | --- | --- |

| 11. | Next Steps | 17 |
| --- | --- | --- |

# 1. Executive Summary

Innovic ERP today is a single 29,000-line HTML file backed by Firebase Firestore. While functional for its current users, the underlying data architecture has a structural concurrency flaw: every collection is stored as a single JSON-serialized document, which means the entire dataset of any module is rewritten every time any user edits any record. At 10–15 concurrent users this manifests as silent data loss, performance degradation, and a hard 1 MB per-collection ceiling that will be hit within 6–12 months at current growth.

This proposal outlines a complete migration to a production-grade web architecture built on Supabase (managed Postgres, authentication, file storage) with a TypeScript-based API and a modern React frontend. The architecture is designed to scale to 100 concurrent users without rearchitecting, costs approximately ₹2,800 per month all-in, and can be delivered in 12 weeks using a strangler-pattern migration (the existing system continues running until each module is verified on the new platform).

Key Outcomes • Concurrency problem eliminated — every record is now atomic and independently editable • Real, enforced role-based access at the database level (Row-Level Security) • Reports and dashboards in seconds, not minutes • Full audit trail, soft delete, and offsite backups on day one • Total monthly cost roughly equal to current Firebase usage at scale • Zero-downtime migration — old system runs in parallel until each module is cut over

### Investment Summary

| Item | Cost |
| --- | --- |
| One-time migration & development (12 weeks) | Quoted separately based on team |
| Recurring infrastructure (15–20 users) | ~₹2,800 / month (~$33) |
| Recurring infrastructure (100 users) | ~₹3,800 / month (~$45) |

# 2. Current System Diagnosis

### What exists today

- Single HTML file (~29,000 lines) containing UI, business logic, and data layer in one document

- 67 Firestore collections covering Sales, Job Cards, Operations, QC, Procurement, Design, CRM, and supporting data

- Firebase Auth for login, Firestore for data, Firebase Storage for files

- All authorization logic lives in browser JavaScript and is therefore bypassable

### The core architectural flaw

Each Firestore "collection" is implemented as a single document with all records serialized into a JSON string field. Every save operation rewrites the entire collection. The relevant code pattern is:

batch.set(docRef, { records: JSON.stringify(data), // entire collection rewritten on every save count: data.length, ... })

### Failure modes already present or imminent

| Failure Mode | Operational Impact |
| --- | --- |
| Concurrent edits to same collection | Last-write-wins; one user's edits silently disappear |
| Collection grows past ~1 MB | Firestore rejects the write entirely; all saves to that module fail |
| Real-time listener fires on any change | Every connected user re-downloads the entire collection — bandwidth and re-render storm |
| Network blip during save | Whole-collection rewrite fails atomically; entire batch of edits is lost |
| Authorization in browser code | Any user can bypass UI restrictions via browser dev tools — no real security |
| Reports and dashboards | Built by pulling all records into memory and aggregating in JavaScript — slow and unreliable |

Important This is a data-shape problem, not a UI problem. Migrating only the frontend (e.g. moving HTML to React) without changing the database structure would deliver no improvement. The migration must happen at the data layer first.

# 3. Target Architecture

The target architecture has three independently deployable components and one managed platform. Each component has a single, well-defined responsibility.

### Component diagram

Browser (User Device) ↓ HTTPS / WebSocket React SPA → hosted on Cloudflare Pages (free) ↓ Fastify API (Node.js + TypeScript) → hosted on Railway / Hetzner ↓ Supabase Pro (Mumbai region) Postgres + Auth + Storage + Realtime + Backups

### Component responsibilities

| Component | Responsibility |
| --- | --- |
| React Frontend | Renders UI, handles forms and navigation, submits user intents to the API. Contains zero business logic. Built with Vite, TypeScript, Tailwind, shadcn/ui, TanStack Query. |
| Fastify API | Owns all business logic: validation, calculations, authorization, transactional integrity. Talks to Supabase as its database. Built with TypeScript, Drizzle ORM, Zod schemas, Pino structured logs. |
| Supabase Postgres | Single source of truth for all transactional and master data. Enforces multi-tenant isolation and role-based access via Row-Level Security policies. Daily backups + 7-day point-in-time recovery. |
| Supabase Auth | Email/password and magic-link authentication, JWT-based session management, multi-factor authentication ready. |
| Supabase Storage | File storage (QC documents, drawings, exports) with same access policies as the database. S3-compatible API. |
| Supabase Realtime | WebSocket streaming of database changes for live screens (Op Entry, machine status, dashboards). Used selectively to avoid overhead. |

### Why this exact stack

- Postgres over Firestore — ERP data is fundamentally relational (SO → JW → JC → Operations → QC → Dispatch). Postgres handles joins, transactions, and reports natively; Firestore does not.

- Row-Level Security — Authorization rules live in the database, not the application. Even a buggy API cannot leak data across companies, departments, or roles.

- TypeScript everywhere — Single language across frontend and backend. Shared validation schemas (Zod) ensure API and UI never disagree on data shapes.

- Drizzle ORM, not Prisma — Lightweight, transparent, raw-SQL escape hatch when needed. No code generation step.

- TanStack Query — Replaces ~2,000 lines of hand-rolled cache/sync logic with declarative hooks. Optimistic updates, retries, deduplication, stale-while-revalidate built in.

- Cloudflare Pages — Free hosting with unlimited bandwidth. Frontend deploys on every git push.

# 4. Why Supabase (Decision Rationale)

Three platforms were evaluated for hosting the Postgres database, authentication, and file storage at the target scale of 15–100 users with 50 GB total data. Costs are normalized to the Mumbai (ap-south-1) region.

### Comparison at scale

| Criterion | Supabase Pro | AWS | Notes |
| --- | --- | --- | --- |
| Monthly cost (your scale) | $26 (~₹2,200) | $60 (~₹5,000) | AWS is 2.3× more at this size |
| Setup time | 1 day | 1–2 weeks | AWS requires VPC, IAM, RDS config, etc. |
| Ongoing ops burden | ~0 hr / month | 5–10 hr / month | Patching, alarms, backups, log retention |
| Database engine | Postgres 15 | Postgres 15 | Identical engine — quality is not compromised |
| Vendor lock-in | Low | Low to medium | Both use standard Postgres + S3 API |
| Auth, Storage, Realtime | Included | Bolt-on | AWS requires Cognito + S3 + AppSync setup |
| Mumbai region | Yes | Yes | Both deliver low latency for India users |
| Scaling ceiling | ~1,000 users | Unlimited | Migration to AWS is straightforward if needed later |

Recommendation Supabase Pro is the recommended platform. AWS would deliver no functional difference at 15–100 users while costing roughly twice as much and requiring permanent operations effort. If usage ever exceeds 1,000 concurrent users (years away), migrating from Supabase to AWS RDS + S3 is a 1-day operation — the data and code are portable by design.

# 5. Database Schema Design

The 67 flat Firestore collections will be consolidated into approximately 30–40 properly normalized Postgres tables. Several Firestore collections are duplicates that the flat data model forced (for example, four separate dispatch tables become one with a direction enum). The new schema is built around a relational spine that mirrors the actual business process flow.

### Core relational spine

clients ──< sales_orders ──< job_work_orders ──< job_cards ──< jc_ops ──< op_log │ ├──< qc_inspections ──< qc_attachments ├──< nc_register └──< dispatch_log vendors ──< purchase_orders ──< po_lines ──< grn ──< grn_lines │ └──> store_transactions items, machines, operators, users ← master tables, referenced everywhere

### Module groups (final table count)

| Module | Tables | Replaces (Firestore Collections) |
| --- | --- | --- |
| Master Data | 7 | companies, users, clients, vendors, items, machines, operators |
| Sales & Production | 6 | salesOrders, jobWorkOrders, jobCards, jcOps, opLog, runningOps |
| Procurement | 5 | purchaseRequests, purchaseOrders, grn, storeTransactions, storeIssues |
| Quality (QC + NC) | 4 | qcProcesses, qcAssignments, qcDocUploads, ncRegister, capaRecords |
| Dispatch & Delivery | 3 | jwDCOutward, jwDCInward, challans, dispatchLog (consolidated with direction enum) |
| Design Tracker | 4 | designProjects, designTasks, designIssues, designWorkLog, designTimeLog, designDCRs, designDCNs |
| CRM | 3 | leads, communications, crmReminders |
| Outsource & Job-Work | 3 | outsourceJobs, ospProcessConfig, ospDC, servicePOs |
| Audit & Logging | 2 | activityLog, trash (replaced by soft delete) |
| Configuration | 4 | dashboardConfig, alertConfig, printTemplates, stuckThresholds, reportTypes |
| TOTAL | ~41 | Replaces 67 Firestore collections |

### Universal table conventions

Every table in the new schema includes the following columns by default. This is non-negotiable — applied via a migration template at table creation time.

- id — UUID primary key (auto-generated)

- company_id — Multi-tenant isolation from day one (free future-proofing if a second factory or client is onboarded)

- created_at, created_by, updated_at, updated_by — Full audit trail on every record

- deleted_at — Soft delete (replaces the current 'trash' collection; nothing is ever truly destroyed)

- Row-Level Security policy — Database-enforced authorization based on company_id and user role

# 6. Migration Plan — 12 Week Roadmap

The migration follows the strangler pattern: the existing HTML system continues running for the entire 12 weeks. New modules are deployed alongside the old system and validated in parallel before each cutover. There is no big-bang weekend cutover and no extended downtime.

### Timeline at a glance

| Phase | Week | Deliverable |
| --- | --- | --- |
| 0 | Pre-kickoff (3 days) | Accounts provisioned, repository created, schema designed and reviewed |
| 1 | Week 1–2 | Foundation — auth, schema deployed, first end-to-end module (Items master) |
| 2 | Week 3 | All master data migrated and editable in new system |
| 3 | Week 4–5 | Op Entry module live (highest-frequency, multi-user pain point) |
| 4 | Week 6–7 | Sales chain — SO, JW, JC fully migrated |
| 5 | Week 8 | Procurement chain — PO, GRN, store transactions |
| 6 | Week 9 | QC, NC register, dispatch |
| 7 | Week 10 | Reports, dashboards, role-based KPIs |
| 8 | Week 11 | Peripheral modules — design tracker, CRM, tools, CAPA, print templates |
| 9 | Week 12 | Final cutover — HTML system goes read-only, new system is sole source of truth |

### Detailed scope per phase

Phase 1 — Foundation (Week 1–2)

- Set up monorepo with pnpm workspaces, TypeScript, ESLint

- Bootstrap Fastify API: Drizzle ORM, Zod validation, Pino structured logs, error handling

- Bootstrap React frontend: Vite, Tailwind, shadcn/ui, TanStack Query, TanStack Router

- Apply complete schema to Supabase (all tables, indexes, RLS policies)

- Implement authentication flow end-to-end (login, JWT propagation, protected routes)

- Build Items master as the reference template for every other module

- Set up CI/CD via GitHub Actions (auto-deploy on merge to main)

- Exit criterion: a user can log in, navigate to Items, perform full CRUD, and the data persists with proper RLS isolation

Phase 2 — Master Data (Week 3)

- Build one-time Firestore export script (dumps all 67 collections to local JSON)

- Build transformation script (flattens JSON-blob structure to per-record rows, generates UUIDs, maps Firebase auth UIDs)

- Build bulk-load script (inserts to Postgres in foreign-key dependency order)

- Migrate users, clients, vendors, items, machines, operators

- Build admin screens for each master entity

- Validate: row counts match, sample records identical, no orphaned references

- Exit criterion: all master data is in Supabase and editable through the new UI; old HTML still serves transactions

Phase 3 — Op Entry (Week 4–5) — Critical Phase

- Migrate jobCards, jcOps, opLog data

- Build Op Entry screen with TanStack Query optimistic updates and Realtime subscription

- Implement server-side validations: cannot exceed planned quantity, cannot skip required QC, etc.

- Run parallel mode for one full week: operators enter data in BOTH systems, end-of-day reconciliation

- After validation passes for 5 consecutive working days, switch operators to new system only

- Exit criterion: operators are exclusively on the new system for Op Entry

Phase 4 — Sales Chain (Week 6–7)

- Migrate sales_orders, sales_order_lines, job_work_orders

- Build SO list, detail, create/edit screens

- Build JW list, detail screens

- Build JC list with filtering by status, machine, operator

- Implement cascade logic server-side: SO status auto-updates from JC completion (fixes existing bug)

- Cutover sales team module-by-module

Phase 5 — Procurement (Week 8)

- Migrate purchase_orders, po_lines, grn, grn_lines, store_transactions

- Build PO/GRN screens with vendor cascade and line-item matching

- Cutover procurement team

Phase 6 — Quality + Dispatch (Week 9)

- Migrate qc_inspections (consolidated from qcProcesses/qcAssignments/qcDocUploads)

- Migrate nc_register, dispatch_log, delivery_challans

- Build QC inspection workflow with file uploads to Supabase Storage

- Cutover QC and dispatch teams

Phase 7 — Reports & Dashboards (Week 10)

- Convert in-memory aggregations to SQL views and materialized views

- Build dashboard with role-based KPI cards

- Build the 5–10 most-used reports

- Add Excel export endpoint via exceljs

Phase 8 — Peripheral Modules (Week 11)

- Design tracker (consolidated from 7 collections to 4 tables)

- CRM: leads, communications, reminders

- Tool issues, store issues, party materials

- CAPA records, print template editor

- Activity log viewer + admin trash recovery

Phase 9 — Final Cutover (Week 12)

- Final delta migration from Firebase (capture last week's data)

- HTML system goes read-only, then archived offline

- Set up monitoring: Better Stack uptime, Supabase metrics, Sentry error tracking

- Verify backups: restore a pg_dump to a test instance, confirm app boots against it

- Document runbook for common operational issues

- Train all users on the new system

# 7. Cost Breakdown

### Recurring monthly cost (15–20 users)

| Item | USD | INR (≈) | Notes |
| --- | --- | --- | --- |
| Supabase Pro | $25 | ₹2,100 | Postgres + Auth + Storage + Realtime + Backups |
| Fastify API hosting (Railway) | $7 | ₹590 | Or Hetzner CCX13 self-managed (~₹450) |
| Cloudflare Pages (frontend) | $0 | ₹0 | Free tier — unlimited bandwidth |
| Cloudflare DNS + WAF | $0 | ₹0 | Free tier |
| Resend (transactional email) | $0 | ₹0 | Free up to 3,000 emails/month |
| Backblaze B2 (offsite backup) | $1 | ₹85 | 50 GB at $0.005/GB |
| Sentry (error tracking) | $0 | ₹0 | Free tier — sufficient for small teams |
| Better Stack (uptime + logs) | $0 | ₹0 | Free tier |
| Domain (amortized) | $1 | ₹100 | Annual cost spread monthly |
| TOTAL | ~$33 | ~₹2,800 | Per month, all-in |

### Scaling cost projection

| User Count | Monthly USD | Monthly INR | Per-user / month |
| --- | --- | --- | --- |
| 15–20 users (today) | $33 | ₹2,800 | ~₹150 |
| 50 users | $38 | ₹3,200 | ~₹64 |
| 100 users (target ceiling) | $45 | ₹3,800 | ~₹38 |

Note: between 50 and 100 users a Supabase compute upgrade adds approximately $10–15/month. No other components require changes within this user range.

# 8. Operating Rules (Non-Negotiable)

These ten rules are written into the project from day one and enforced in code review. Violating any one of them is how production systems rot over time. They are deliberately strict.

1. No business logic in the frontend.

The React app shows data and submits intents. Validation, calculations, and authorization all live server-side. The browser is hostile and inspectable; nothing in it can be trusted.

2. Every write goes through a service layer.

Routes never call the ORM directly. Service functions encapsulate business logic and are independently testable. Without this discipline, logic spreads across hundreds of route handlers and becomes unmaintainable.

3. Every table has company_id, soft delete, audit columns, and an RLS policy.

No exceptions. Multi-tenancy from day one is free future-proofing; soft delete makes data recoverable; audit columns answer 'who changed this and when' without forensics.

4. Daily automated pg_dump to a second provider, with monthly restore drills.

Backblaze B2 holds the offsite copy. Untested backups are not backups — restore is verified the first Monday of every month.

5. All times stored as timestamptz in UTC, displayed in IST.

The single most common ERP bug ('the report says yesterday but it's still today') is prevented by convention and never revisited.

6. No SELECT * in production code. No N+1 queries.

Drizzle makes both visible. Both are rejected in code review. They look harmless until the table has 100,000 rows.

7. Structured JSON logs from day one.

When the system breaks at 11pm with 80 users active, the team needs grep-able structured logs, not console.log spam.

8. No hard deletes — only soft deletes.

deleted_at is set; the row is excluded from queries by default. Hard deletes happen only via an admin maintenance script after a backup is taken.

9. Schema changes via Drizzle migrations only.

No manual SQL in the Supabase Studio for production data. All migrations are version-controlled and reviewed before deployment.

10. Secrets in environment variables, never in code.

Supabase service keys, JWT secrets, third-party API keys live in Railway/Hetzner env vars or Doppler. The repository is treated as if it were public.

# 9. Risks & Mitigation

Honest assessment of where this architecture and migration plan can break, and the mitigation built in for each. Risks are listed in descending order of likelihood at your scale.

| Risk | Severity | Trigger | Mitigation |
| --- | --- | --- | --- |
| Data migration mismatch | High | Firebase JSON-blob shape varies across collections; some records have inconsistent fields | Migration scripts include validation pass; parallel-run period of 1 week per major module catches discrepancies before cutover |
| User adoption friction | Medium | Operators resist UI changes after years on the HTML system | New UI mirrors existing flows where possible; module-by-module cutover; training session before each phase |
| Scope creep during migration | Medium | Stakeholders ask for new features mid-migration | Strict rule: feature parity first, new features only after Week 12 cutover. New requests logged as backlog items |
| Supabase outage | Low | Supabase regional incident (rare; SLA 99.9%) | Daily offsite backup means worst case is restoring to a fresh Postgres instance and rerouting; ~1 hour RTO |
| API server failure | Low | Single VPS hardware failure | Stateless API auto-restarts; Railway provides automatic recovery; can scale to 2 instances when needed (₹500/mo extra) |
| Postgres connection exhaustion | Low | Too many open connections under load | Supabase includes PgBouncer connection pooler; configured on day one |
| File storage cost overrun | Low | QC documents grow faster than projected | 100 GB storage included on Supabase Pro; alarm at 80 GB; storage tier upgrade cost is linear and predictable |
| Vendor lock-in concern | Very Low | Future need to migrate off Supabase | Supabase = standard Postgres + S3-compatible storage; pg_dump + bucket copy = full migration in one day |

# 10. Deliverables & Acceptance Criteria

### Final deliverables

| Deliverable | Description |
| --- | --- |
| Source Code Repository | Private GitHub repository with monorepo (web, api, shared types, migration scripts). Owned by client. MIT-licensed dependencies only. |
| Production Deployment | Live system at chosen domain, with auto-deploy from main branch via GitHub Actions |
| Database Schema | Complete Drizzle schema definitions, migration files, RLS policies, seed data scripts |
| Migration Scripts | One-time export/transform/load scripts from Firebase to Supabase, with validation reports |
| Operations Runbook | Documentation covering deployment, backup/restore, common issues, monitoring dashboards, secret rotation |
| API Reference | OpenAPI specification auto-generated from Zod schemas, served at /docs endpoint |
| User Training Material | Module-by-module video walkthroughs and quick-reference PDF for end users |
| Monitoring Dashboard | Better Stack uptime monitoring, Sentry error tracking, Supabase observability — all configured and accessible |

### Acceptance criteria (per phase)

Each phase has objective acceptance criteria that must be met before proceeding to the next. The client signs off in writing before any phase is considered complete.

- All migrated records match Firebase source data exactly (count and content validation report attached)

- All RLS policies tested with at least 3 user roles; cross-company access attempts are logged and blocked

- All forms submit, validate server-side, and return accurate error messages for invalid input

- All reports return correct figures cross-checked against the existing HTML system for the same date range

- Backup and restore drill completed successfully on a test environment

- Load test passes for 25 concurrent users sustaining 1 request/second per user without errors

# 11. Next Steps

If this proposal is approved in principle, the following actions kick off the engagement:

Week 0 — Pre-Kickoff (3 working days) 1. Sign off on this proposal and architecture 2. Provision accounts: Supabase Pro, Railway (or Hetzner), Cloudflare, GitHub, Resend 3. Identify primary stakeholder for each module (sales, production, QC, procurement, design) 4. Schedule weekly sync (30 min) to review previous week's progress and unblock decisions 5. Finalize domain name and email setup 6. Schedule training windows aligned with each phase cutover

### Decisions still needed from client

- API hosting choice: Railway (managed, $7/mo) or Hetzner CCX13 (self-managed, ~₹450/mo)

- Domain name to use for the new system

- Email-from address for transactional emails (e.g., system@innovic.in)

- Initial admin user list (full name, email, role)

- Confirmation that current Firebase project access can be granted to migration scripts (read-only sufficient)

- Any compliance or audit requirements not already covered (currently none assumed)

This proposal is valid for 30 days from the document date. All architecture decisions are reversible — at any point during the engagement, the client retains full ownership of the source code, database schema, and all data, and can move the entire system to alternative infrastructure with no vendor-locked components.

End of Proposal